## Sheet1
WBS Compucom Tracker Portal
Compucom Tracker Web Portal Development Project Schedule
(Compucom Software Ltd.)
|  |  | Project Lead | Rajseh Arora
|  |  | Project Start Date | 2017-01-16
|  |  | Today's Date | 2017-12-30
S.No. | Task ID | Task Description | Assigned To | Start Date | End Date
1 | 1.1 | Project Initiation
|  | Identify business need | Manoj A | 2017-01-16 | 2017-01-17
|  | Develop preliminary budget | Manoj A | 2017-01-18 | 2017-01-19
|  | Identify preliminary return on investment | Manoj A | 2017-01-20 | 2017-01-21
|  | Requirement Study | Manoj A, Rajesh A | 2017-01-23 | 2017-01-28
|  | Project Kick off | Manoj A | 2017-01-29 | 2017-01-29
| 2.1 | Project Planning
|  | Project Plan writing | Manoj A | 2017-01-20 | 2017-01-28
|  | SRS Prepration | Rajesh A | 2017-01-20 | 2017-01-28
|  | Database Design | Rajesh A | 2017-01-30 | 2017-02-04
|  | UI Design |  | 2017-01-30 | 2017-02-04
| 3.1 | User Registration Module
|  | Form Design | Alok K | 2017-02-06 | 2017-02-07
|  | Detabase Design | Rajesh A | 2017-02-08 | 2017-02-09
|  | Design Review | Manoj A | 2017-02-10 | 2017-02-10
|  | Development | Rajesh A | 2017-02-13 | 2017-02-23
|  | Code Review | Manoj A | 2017-02-24 | 2107-02-27
|  | Testing | Alok K | 2017-02-28 | 2017-03-03
|  | Deployment of Module | Manoj A | 2017-03-05 | 2017-03-05
| 4.1 | Tracker Registration Module
|  | Form Design | Alok K | 2017-03-06
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-04-15
| 5.1 | Live Tracking module
|  | Form Design | Alok K | 2017-04-17
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-06-03
History Module For Tracking
|  | Form Design | Alok K | 2017-06-05
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-07-15
Dashboard For User Status Tracking Module
|  | Form Design | Alok K | 2017-07-17
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-08-05
Trip Report Module
|  | Form Design | Alok K | 2017-08-08
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-08-19
SMS Integration Module
|  | Form Design | Alok K | 2017-08-21
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-09-23
Mobile Notification Module
|  | Form Design | Alok K | 2017-09-25
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-11-15
Android App (Basic) Module
|  | Form Design | Amit S | 2017-02-16
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Amit S
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-09-23
Notification Display Module
|  | Form Design | Amit S | 2017-09-25
|  | Detabase Design | Rajesh A
|  | Review | Manoj A
|  | Development | Rajesh A
|  | Testing | Alok K
|  | Deployment of Module | Amit S |  | 2017-11-15
Testing
|  | Testing | Alok K | 2017-11-16 | 2017-11-30
Bug Fixing
|  | Bug Fixing |  | 2017-12-01 | 2017-01-19
Testing & Deployment
|  | Testing & Deployment |  | 2017-12-20 | 2017-12-29
Release
|  | Release |  | 2017-12-30 | 2017-12-30