## v1.0
Annexure1: Project Estimation COMPUCOM TRACKER
Functional Areas:
Sr. # | Functional Area | Number of Objects | No. of fields/features | Total Objects | Complexity
[5 empty] | High | Medium | Low
1 | Home Page
1.1 | Design Of Interface | 5 | 1 | 5 | 2 | 2 | 1
1.2 | Layout | 1 | 1 | 1 | 1 | 0 | 0
1.3 | Login | 1 | 2 | 2 | 0 | 1 | 0
1.4 | Test & Review | 10 | 1 | 10 | 5 | 3 | 2
2 | Project Initiation
2.1 | Requirenment Understanding
2.2 | Feasibility Study
3 | Project Planning
3.1 | Plan Creation
4 | User Registeration
4.1 | Design of Interface | 2 | 10 | 20 | 2 | 2 | 6
4.2 | Layout | 1 | 2 | 2 | 1 | 1 | 2
4.3 | Edit Profile | 1 | 5 | 5 | 0 | 1 | 4
4.4 | Track Config | 1 | 3 | 3
5 | Track Registeration
5.1 | Design of Interface | 1 | 3 | 3 | 0 | 2 | 1
5.2 | Layout | 2 | 1 | 2 | 0 | 1 | 1
5.3 | Approve Registeration | 1 | 1 | 1 | 1 | 0 | 0
6 | Live Tracking
6.1 | Design of Interface | 1 | 3 | 3 | 1 | 2 | 0
6.2 | Layout | 3 | 3 | 9 | 2 | 2 | 5
6.3 | Location Track Display | 1 | 3 | 3 | 0 | 3 | 0
7 | History Module
7.1 | Design of Interface | 2 | 4 | 8 | 2 | 2 | 4
7.2 | Layout | 4 | 1 | 4 | 0 | 0 | 4
7.3 | Track History date-wise | 1 | 1 | 1 | 0 | 1 | 0
7.4 | Export History | 2 | 1 | 2 | 0 | 2 | 0
8 | Dash Board
8.1 | Design of Interface | 3 | 2 | 6 | 0 | 2 | 4
8.2 | Layout | 1 | 1 | 1 | 0 | 0 | 1
8.3 | Last Active Report(Day-wise & Group-wise) | 1 | 1 | 1 | 0 | 1 | 0
9 | Trip Report
9.1 | Design of Interface | 3 | 2 | 6 | 0 | 2 | 4
9.2 | Layout | 1 | 1 | 1 | 0 | 0 | 1
9.3 | Durational Device Trip Report | 2 | 1 | 2 | 0 | 1 | 1
10 | SMS Integration
10.1 | Design of Interface | 1 | 1 | 1 | 0 | 1 | 0
10.2 | SMS Integration | 1 | 2 | 2 | 0 | 2 | 0
11 | Mobile Notification
11.1 | Design of Interface | 1 | 3 | 3 | 2 | 1 | 0
11.2 | App Notifications Functionality | 1 | 1 | 1 | 0 | 1 | 0
| TOTAL |  |  | 108 | 19 | 36 | 41
Size Calculation:
Assumptions:
Sr. # | Task | No. of Mandays
1 | Analysis, Design, Development & Testing of Low Complexity object | 2
2 | Analysis, Design, Development & Testing of Medium Complexity object | 4
3 | Analysis, Design, Development & Testing of High Complexity object | 7
Project Sizing
Sr. # | Objects | Number | Unit | No of Mandays
1 | Highly Complex | 100 | 7 | 700
2 | Medium Complex | 75 | 4 | 300
3 | Low Complex | 38 | 2 | 76
| Total Objects | 213 |  | 1076
| Client deadline | 210 | (working Days)
| Man heads Required | (Total Mandays/Client Deadline) |  | 5.1238
Cost Calculation:
Sr. # | Resource | Number | Hour/Day | Total Days | Total Hours | Total ManHours | Rate/Hour | Total Cost
1 | Project Manager | 1 | 8 | 210 | 1680 | 1680 | 600 | 1008000
2 | System Analyst cum Architect / Developer | 1 | 8 | 210 | 1680 | 1680 | 500 | 840000
4 | Developer | 2 | 8 | 210 | 1680 | 3360 | 350 | 1176000
5 | Tester & Desinger | 1 | 8 | 210 | 1680 | 1680 | 300 | 504000
| Total Manpower Cost |  |  |  |  | 8400 |  | 3528000
| Infrastructure Cost + Logistics Costs(@ 10% Manpower Cost) | [6 empty] | 352800
| Grand Total | [6 empty] | 3880800

## Sheet2
Estimation Assumptions
S # | Complexity | GUI Components* | Database Components~ |  |  |  | Others
|  |  | SP | Trigger | Tables | Views | Third Party Software Integrations | Exisiting Module Integration | Hardware Integration
1 | High | >=10 | SLOC>20, Involvement of 5 or more Tables/Calling of 3 or more SPs/2 databases | SLOC>20, Involvement of 5 or more Tables/Calling of 3 or more SPs/2 databases | Database comprising of 50 or more data tables with at least Level 3 Normalization | SLOC>20, Involvement of 5 or more Tables
2 | Medium | >4 & <10 | 10<SLOC>20, Involvement of at the most 4 Tables/ calling of at the most 2 other SPs | 10<SLOC>20, Involvement of at the most 4 Tables/ calling of at the most 2 other SPs | Database comprising of at least 20 & at the most 50 data tables with Level 3 Normalization | 10<SLOC>20, Involvement of at the most 4 Tables
3 | Low | <4 | SLOC<10, Involvement of at the most 2 Tables | SLOC<10, Involvement of at the most 2 Tables | Database comprising of at the most 20 data tables with at most Level 2 Normalization | SLOC<10, Involvement of at the most 2 Tables
*Includes validations, implementation of other technologies, viz. anthem, ajax on the fields
~Includes deisgn, development & unit testing of Stored Procedures, Views, Triggers, Tables, etc.