## Sheet1
WBS Compucom Tracker Portal
Compucom Tracker Web Portal Development Project Schedule
(Compucom Software Ltd.)
|  |  | Project Lead | Rajseh Arora
|  |  | Project Start Date | 2017-01-16
|  |  | Today's Date | 2017-12-30
S.No. | Task ID | Task Description | Assigned To | Start Date | End Date
1 | 1.1 | Project Initiation
|  | Identify business need | Manoj A | 2017-01-16 | 2017-01-17
|  | Develop preliminary budget | Manoj A | 2017-01-18 | 2017-01-19
|  | Identify preliminary return on investment | Manoj A | 2017-01-20 | 2017-01-21
|  | Requirement Study | Manoj A, Rajesh A | 2017-01-23 | 2017-01-28
|  | Project Kick off | Manoj A | 2017-01-29 | 2017-01-29
2 | 2.1 | Project Planning
|  | Project Plan writing | Manoj A | 2017-01-20 | 2017-01-28
|  | SRS Prepration | Rajesh A | 2017-01-20 | 2017-01-28
|  | Database Design | Rajesh A | 2017-01-30 | 2017-02-04
|  | UI Design |  | 2017-01-30 | 2017-02-04
3 | 3.1 | User Registration Module
|  | Form Design | Alok K | 2017-02-06 | 2017-02-07
|  | Detabase Design | Rajesh A | 2017-02-08 | 2017-02-09
|  | Design Review | Manoj A | 2017-02-10 | 2017-02-10
|  | Development | Rajesh A | 2017-02-13 | 2017-02-23
|  | Code Review | Manoj A | 2017-02-24 | 2107-02-27
|  | Testing | Alok K | 2017-02-28 | 2017-03-03
|  | Deployment of Module | Manoj A | 2017-03-06 | 2017-03-06
4 | 4.1 | Tracker Registration Module
|  | Form Design | Alok K | 2017-03-07 | 2017-03-10
|  | Detabase Design | Rajesh A | 2017-03-14 | 2017-03-17
|  | Design Review | Manoj A | 2017-03-20 | 2017-03-21
|  | Development | Rajesh A | 2017-03-22 | 2017-04-03
|  | Code Review | Manoj A | 2017-04-05 | 2017-04-07
|  | Testing | Alok K | 2017-04-10 | 2017-04-13
|  | Deployment of Module | Amit S | 2017-04-17 | 2017-04-18
5 | 5.1 | Live Tracking module
|  | Form Design | Alok K | 2017-04-19 | 2017-04-26
|  | Detabase Design | Rajesh A | 2017-04-27 | 2017-05-02
|  | Design Review | Manoj A | 2017-05-03 | 2017-05-05
|  | Development | Rajesh A | 2017-05-08 | 2017-05-22
|  | Code Review | Manoj A | 2017-05-23 | 2017-05-26
|  | Testing | Alok K | 2017-05-29 | 2017-05-31
|  | Deployment of Module | Amit S | 2017-06-01 | 2017-06-02
6 | 6.1 | History Module For Tracking
|  | Form Design | Alok K | 2017-06-05 | 2017-06-09
|  | Detabase Design | Rajesh A | 2017-06-12 | 2017-06-15
|  | Design Review | Manoj A | 2017-06-16 | 2017-06-21
|  | Development | Rajesh A | 2017-06-22 | 2017-07-05
|  | Code Review | Manoj A | 2017-07-06 | 2017-07-07
|  | Testing | Alok K | 2017-07-10 | 2017-07-12
|  | Deployment of Module | Amit S | 2017-07-13 | 2017-07-14
7 | 7.1 | Dashboard For User Status Tracking Module
|  | Form Design | Alok K | 2017-07-17 | 2017-07-19
|  | Detabase Design | Rajesh A | 2017-07-20 | 2017-07-24
|  | Design Review | Manoj A | 2017-07-25 | 2017-07-26
|  | Development | Rajesh A | 2017-07-27 | 2017-07-31
|  | Code Review | Manoj A | 2017-08-01 | 2017-08-01
|  | Testing | Alok K | 2017-08-02 | 2017-08-03
|  | Deployment of Module | Amit S | 2017-08-04 | 2017-08-04
8 | 8.1 | Trip Report Module
|  | Form Design | Alok K | 2017-08-08 | 2017-08-09
|  | Detabase Design | Rajesh A | 2017-08-10 | 2017-08-11
|  | Design Review | Manoj A | 2017-08-14 | 2017-08-14
|  | Development | Rajesh A | 2017-08-16 | 2017-08-21
|  | Code Review | Manoj A | 2017-08-22 | 2017-08-22
|  | Testing | Alok K | 2017-08-23 | 2017-08-24
|  | Deployment of Module | Amit S | 2017-08-25 | 2017-08-25
9 | 9.1 | SMS Integration Module
|  | Form Design | Alok K | 2017-08-28 | 2017-08-29
|  | Detabase Design | Rajesh A | 2017-08-29 | 2017-08-31
|  | Design Review | Manoj A | 2017-09-01 | 2017-09-01
|  | Development | Rajesh A | 2017-09-04 | 2017-09-15
|  | Code Review | Manoj A | 2017-09-18 | 2017-09-18
|  | Testing | Alok K | 2017-09-19 | 2017-09-22
|  | Deployment of Module | Amit S | 2017-09-23 | 2017-09-23
10 | 10.1 | Mobile Notification Module
|  | Form Design | Alok K | 2017-09-25 | 2017-09-28
|  | Detabase Design | Rajesh A | 2017-09-29 | 2017-10-06
|  | Design Review | Manoj A | 2017-10-09 | 2017-10-10
|  | Development | Rajesh A | 2017-10-11 | 2017-10-26
|  | Code Review | Manoj A | 2017-10-27 | 2017-11-01
|  | Testing | Alok K | 2017-11-02 | 2017-11-10
|  | Deployment of Module | Amit S | 2017-11-13 | 2017-11-15
11 | 11.1 | Android App (Basic) Module
|  | Form Design | Amit S | 2017-03-13 | 2017-04-17
|  | Web Service Development | Rajesh A | 2017-04-18 | 2017-05-01
|  | Design Review | Manoj A | 2017-05-02 | 2017-06-25
|  | Development | Amit S | 2017-05-26 | 2017-07-31
|  | Code Review | Manoj A | 2017-08-01 | 2017-08-25
|  | Testing | Alok K | 2017-08-28 | 2017-09-15
|  | Deployment of Module | Amit S | 2017-09-18 | 2017-09-22
12 | 12.1 | Notification Display Module
|  | Form Design | Amit S | 2017-09-25 | 2017-10-06
|  | Detabase Design | Rajesh A | 2017-10-09 | 2017-10-13
|  | Design Review | Manoj A | 2017-10-16 | 2017-10-18
|  | Development | Amit S | 2017-10-23 | 2017-11-07
|  | Code Review | Manoj A | 2017-11-08 | 2017-11-09
|  | Testing | Alok K | 2017-11-10 | 2017-11-14
|  | Deployment of Module | Amit S | 2017-11-15 | 2017-11-15
13 | 13.1 | Testing
|  | Testing | Manoj A, Alok K | 2017-11-16 | 2017-11-30
14 | 14.1 | Bug Fixing
|  | Bug Fixing | Rajesh A, Amit S | 2017-12-01 | 2017-01-19
15 | 15.1 | Testing & Deployment
|  | Testing & Deployment | Manoj A | 2017-12-20 | 2017-12-29
16 | 16.1 | Release
|  | Release | Manoj A | 2017-12-30 | 2017-12-30